## POA&M
Plan of Action and Milestones (POA&M)
| System Name | KBGH Surgical System |  |  | Date of this POA&M |  | November 4th, 2019
| Company/Organization Name |  |  |  | Date of Last Update |  | November 9th, 2019
Date of Original POA&M
ISSO Information
| Name | Caleb Donkoh-Moore
| Phone | 571-332-0714
| Email | cdonkormore@gmail.com
Item Identifier | Security Control Name | Control ID | Weakness | POC | Scheduled Completion Date | Milestones with Completion Dates | Changes to Milestones | Weakness/ Deficiency Identified by | Risk Level (Low/Med/High) | Estimated Cost | Status
Assmessment | Access Control | AC -1 | Organizational system access control documentation failed to develop procedures to facilitate the implementation of access control policy and its associated access controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Admin | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | Audit and Accountability | AU - 1 | System audit and accountability documentation failed to develop procedures to facilitate the implementation of audit and accountablity policy and its associated audit and accountability controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Admin | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | Identification and Authentification | IA-1 | The system identification and authentication documentation failed to develop procedures to facilitate the implementation of identification and authentication policy and its associated identification and authentication controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Admin | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | System Communication Protection | SC - 1 | The System Communication Protection control documentation failed to develop procedures to facilitate the implementation of system communication protection policy and its associated system communication protection controls. The documentation also failed to define roles to whom the procedures are to be disseminated. | System Owner | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | Security Assessment and Authorization | CA - 1 | The system security assessment and authorization documentation failed to develop procedures to facilitate the implementation of security assessment and authorization policy and its associated controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Owner | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | Planning | PL - 1 | System planning documentation failed to develop procedures to facilitate the implementation of the planning policy and its associated controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Owner | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | Risk Assessment | RA - 1 | The system risk assessment control documentation failed to develop procedures to facilitate the implementation of risk assessment policy and its associated assessment controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Owner | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | System and Services Acquisition | SA - 1 | The system and services acquisition documentation failed to develop procedures to facilitate the implementation of the system and services acquisition policy and its associated system and services acquisition controls. The documentation also failed to define roles to whom the procedures are to be disseminated | Sytem Admin | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing
Assmessment | Program Management | PM - 1 | The program management documentation failed to develop procedures to facilitate the implementation of program management policy and its associated controls. The documentation also failed to define roles to whom the procedures are to be disseminated | System Owner | November 13th, 2019 | December 13th, 2019 | N/A | Caleb Donkoh-Moore | High | 0 | Ongoing

## Column Desc
Column | Heading | Contents—How to Complete
1 | Item Identifier | A unique weakness identifier used to track and correlate weaknesses that are ongoing throughout quarterly submissions within the Organization. The numbering schema for the weakness identifier will be determined by the organization.
2 | Weaknesses or Deficiency | A weakness or deficiency represents any program or system-level information security vulnerability that poses an unacceptable risk of compromising confidentiality, integrity, or availability of information. Describe weakness or deficiency identified by certification/validation testing, annual program review, IG independent evaluation, or any other work done by or on behalf of the Service/Agency. Sensitive descriptions are not necessary, but sufficient detail must be provided to permit oversight and tracking.
3 | IT Security Control Mapping | The Security Controls are listed in the NIST SP 800-53 and shall directly relate to the weakness identified in Column 2. For a security weakness found by means other than a security controls assessment (e.g., vulnerability test), map the deficient function into the applicable security control.
4 | Point of Contact (POC) | A POC is the organization or title of the position within the Organization that is responsible for the mitigation of the weakness. Assigned responsible individuals shall be identified by name as well as organization/title.
5 | Resources Required | Estimated funding and/or manpower resources required for mitigating a weakness. The source and type of funding (current, new, or reallocated) and any funding obstacles should be noted. Note: Be sure to include the total funding requirements in the Security Costs field in Column 13 of the POA&M.
6 | Scheduled Completion Date | Completion dates shall be determined based on a realistic estimate of the amount of time it will take to procure/allocate the resources required for the corrective action and implement/test the corrective action. Once assigned, this date shall not be changed. If a security weakness is resolved before or after the originally scheduled completion date, the actual completion date shall be placed in the Status field. Note: This column should never be left blank, or marked TBD or Unknown. A date must be provided unless the risk is accepted. If risk is accepted, enter N/A.
7 | Milestones with Completion Dates | Milestones with completion dates outline the specific high-level steps to be executed in mitigating the weakness and the estimated completion date for each step. Initial milestones and completion dates should not be changed. Changes to milestones should be placed in the Changes to Milestones field.
8 | Changes to Milestones | Changes to milestones indicate the new estimated date of a milestone’s completion if the original date is not met. The new date and reason for the change in milestone completion should be recorded. No changes should be made to the original data recorded in columns 6 and 7.
9 | Weakness or Deficiency Identified By | This column indicates the source of the weakness (e.g., security controls assessment, penetration test, IG audit, certification testing), the reviewing agency/organization, and the date that the weakness was identified. For example: Quarterly internal security controls review on December 10, 2011
10 | Status | The status field indicates the stage or state of the weakness in the corrective process cycle. The terms available for specifying the Status are: Completed, Ongoing, Delayed, or Planned. The Completed status should be used only when a weakness has been fully resolved and the corrective action has been tested. When listing items as “Completed,” also include the date of completion in this column. Note: In order for the DAA to accept the risk of an identified weakness, the PM office must document and submit a [Mitigation Strategy Report] addressing all implemented/inherited countermeasures and mitigating factors. A recommendation will be made and submitted to the DAA for approval. Once the DAA approves, the weakness may be listed as risk accepted on the POA&M to include the date the decision was made. Solutions to address the risk should be periodically reviewed to eventually close the finding out when possible.
11 | Comments | Include any amplifying or explanatory remarks that will assist in understanding other entries relative to the identified weakness(es). Also include mitigating factors that will lessen the risks to the system and the network. Recommendations to downgrade a finding based on implemented/inherited mitigations should be listed here as well. The ‘Comments’ column shall also be used if there is a delay or change in a Milestone or Scheduled Completion Date. Additionally, the ‘Comments’ column shall identify other, non-funding-related, obstacles and challenges to resolving the weakness (e.g., lack of personnel or expertise, or developing new system to replace insecure legacy system).
12 | Risk Level | The risk level is a ranking (HIGH, MEDIUM, LOW) that determines the impact of a vulnerability, if exploited, to the system, data, and/or program.
13 | Estimated Cost | The estimated cost of correcting the weakness or deficiency. The total estimated cost (arrived at by adding up the individual estimated costs of correcting each weakness or deficiency) is entered in the Security Costs box in Section 1.